## Sheet1
TASK | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Menus | bar: 9 to 10
Movement | bar: 2
Eating | bar: 2 to 3
Gen board | bar: 2 to 3
Chances for number | bar: 5 to 6
Game GUI | bar: 10
Difficuity | bar: 8 to 9
Single Player | bar: 3 to 4
Mutiplayer | bar: 5 to 6
Different Modes | bar: 12 to 13
Debugging | bar: 5 to 7; 12 to 14; 18 to 19
Options | bar: 7
Different Keypress | bar: 2; 11
Highscore | bar: 7 to 8
Tutorial | bar: 16 to 17
Hiniting | bar: 5 to 6
Players | bar: 15 to 16
REPORT | bar: 20
Presentation | bar: 20